## Slide 1
ProofShape
Phone-Based 3D Capture and Inspection for Manufactured Parts
CS595 Capstone Project Proposal · Fall 2026
San Francisco Bay University
Team: Tabeen · Mamadou · Yashi
Phone photos of a part
on a printed reference sheet
Metric 3D model
in the browser
Pass / Fail / Rescan / Unverifiable
report with deviation heatmap
September 2026
Tabeen
Notes: TIMING: 45 seconds. Presenter: [Team member 1]. OPENING LINE (say it almost exactly like this): "ProofShape turns a smartphone into a coarse 3D inspection tool. A supplier puts a part on a printed sheet, takes about twenty photos, and gets back a measured 3D model and a pass or fail report, before the part ships." Then point at the three boxes and walk left to right: photos, model, report. That is the whole product in one line. Say clearly: "Our must-have deliverable is the middle box. Photos in, metric 3D model out. Everything to the right of it is built on top and is scoped so it can be cut without losing the project." DO NOT open with the research angle. Open with the working product. If the room is small, say the team names out loud here and skip most of slide 2.

## Slide 2
Team Members
Three members, three lanes; everyone presents and everyone can run the demo
Tabeen
Lane 1 · Capture front end
Owns what the supplier sees: the phone capture experience, the guidance arrow, the 3D viewer and the report page.
Mamadou
Lane 2 · Reconstruction backend
Owns the GPU service: board detection, multi-view reconstruction, mesh fusion, provenance and latency.
Yashi
Lane 3 · Inspection and truth
Owns correctness: CAD registration, verdict logic, printed specimens, caliper ground truth and testing.
Lane owners are proposed here and confirmed by the team this week. Each lane has a named backup so no milestone depends on one person.
Tabeen
Notes: TIMING: 30 seconds. Keep this fast. Each person says their own name and one phrase, in card order: - [Team member 1]: "I own what the person holding the phone sees." - [Team member 2]: "I own the GPU service that turns the photos into a model." - [Team member 3]: "I own whether the numbers are right." Say once: "Lane owners are proposed, not final. We confirm them this week, and every lane has a backup so no milestone depends on one person." Do not read the cards aloud. The audience can read.

## Slide 3
Roles of Each Team Member (1/2)
Capture front end and reconstruction backend
Tabeen · Lane 1 · Capture front end
Estimated 97 hours
Progressive web app in TypeScript: live camera, HTTPS upload, session link handling
On-device frame gate: blur (Laplacian variance), exposure, duplicate detection
Gyro overlay, next-view scoring, and the capture agent conversation view
three.js viewer for the model, heatmap and observed / unobserved map
Condition report page; testing on one iPhone and one Android phone
Mamadou · Lane 2 · Reconstruction backend
Estimated 97 hours
RunPod GPU pod, Docker image, FastAPI service, one-command startup
ChArUco board detection: metric camera pose per frame, scale, QR code
VGGT integration, with MASt3R and COLMAP fallbacks behind one flag
Segmentation, TSDF fusion, mesh cleanup, GLB export
Per-vertex provenance; generative shape completion; the agent tool-calling loop
Tabeen
Notes: TIMING: 60 seconds. Presenter: [Team member 1] for the left column, [Team member 2] for the right. Left column, the point to land: the phone does real work before anything is uploaded. The local gate rejects blurry, dark and duplicate frames on the device, with a reason shown to the user. That keeps the upload small and the reconstruction clean. Right column, the point to land: the backend is one Docker image on one rented GPU pod. Board detection gives a metric camera pose for every frame, then the reconstruction model turns the frames into geometry. Say once: "The reconstruction model sits behind one config flag. If our first choice underperforms we switch to the second or third without touching anything else." LIKELY QUESTION: "How did you arrive at the hours?" ANSWER: "We started from what each person actually has and worked backwards. We commit nine hours a week each, about a hundred and sixteen across the semester, and all three lanes land at a hundred and fifteen. We raised that from eight hours specifically to fund the generative-AI work." If asked why next-view scoring sits in the capture lane rather than the backend: "It is a guidance feature, the capture lane already owns guidance, and it runs on the processor rather than the graphics card, so no GPU work crosses the boundary."

## Slide 4
Roles of Each Team Member (2/2)
Inspection and truth, plus shared responsibilities
Yashi · Lane 3 · Inspection and truth
Estimated 97 hours
CAD registration: FPFH + RANSAC, robust ICP, orientation-ambiguity check
Deviation heatmap and verdict logic; evaluating whether the agent beats the deterministic policy
Ingestion pre-check against the measured noise floor (σ_floor)
Printer characterization, printed specimens, caliper ground truth
Accuracy, planted-defect, robustness and usability tests
Shared responsibilities
Estimated 54 hours, all members
Progress presentation to the class every two weeks, seven in total
Milestone reports and the final written report
Presentations: everyone presents, everyone can run the demo
Recorded backup demo before the final presentation
Capacity. Each member commits 9 hours a week, about 116 across the semester. All three lanes land at 115.
Scope rule. Tier 1 takes the first half of every lane's hours and is never cut. Tier 3 starts only after Tier 2 is done.
Tabeen
Notes: TIMING: 60 seconds. Presenter: [Team member 3] for the left column, then whoever opened for the callout. Left column, the point to land: this lane is what separates a demo from an inspection tool. Anyone can show a 3D model on screen. Proving the model is accurate to within a known error needs printed parts, calipers and a measured noise floor. Explain sigma-floor in one sentence, because it comes back on slides 5, 7 and 8: "Sigma-floor is the smallest deviation our method can distinguish from its own noise. We measure it, we do not assume it." Right column: read only two bullets, the biweekly progress presentation and the recorded backup demo. On the biweekly presentation, say: "That is seven presentations across the semester. We budgeted eighteen hours for them and built a fixed four-slide template, so preparing one is assembly rather than a scramble." THE CALLOUT IS THE MOST IMPORTANT SENTENCE ON THIS SLIDE. Say it out loud: "Tier 1 takes the first half of every lane's hours and is never cut. We do not start the optional work until the inspection layer is done." That single sentence answers most scope questions before they are asked.

## Slide 5
Why We Chose This Topic
A real inspection gap, and a project shaped so a working product exists at every milestone
The problem
Parts shipped out of spec cost shipping twice plus days to weeks of delay
Coordinate measuring machines are accurate but lab-bound
An emailed photo measures nothing in 3D; a supplier's own scan file is only as trustworthy as the supplier
No sub-minute, phone-only, quantitative check exists at the workbench
Why it fits a capstone
A usable product: phone + printed sheet + browser; no app install, no special hardware
Real computer vision and deep learning: learned multi-view reconstruction, CAD registration, uncertainty
Full-stack engineering: PWA, GPU service, Docker, testing on real phones
Three delivery tiers guarantee a working product at every milestone
Honest scope: millimetre-class checks that complement CMM inspection, never replace it
Tier 1 · Must work
Phone photos → metric 3D model in the browser
Tier 2 · Should work
CAD alignment, deviation heatmap, Pass / Fail / Rescan / Unverifiable
Tier 3 · Could work
Defect-aware guidance, session integrity checks, richer agent coaching
Yashi
Notes: TIMING: 2 minutes. This is the persuasion slide. Slow down here. THE PROBLEM, told as a story rather than four bullets: "A buyer orders a machined bracket. It arrives out of spec. Now they pay shipping twice and lose days or weeks, and there is no record of what the part looked like when it left the supplier. The tool that would have caught it, a coordinate measuring machine, costs a lot and lives in a lab. The tool the supplier actually has is a phone, and a photo measures nothing in three dimensions." Then: "That gap is what we are building into. Phone, printed sheet, browser. No app install, no special hardware." WHY IT FITS A CAPSTONE, pick three and say them plainly: - It is a usable product, not a notebook of experiments. - It uses real computer vision and deep learning: learned multi-view reconstruction, CAD registration, uncertainty estimation. - It is full stack: a web app, a GPU service, Docker, and testing on real phones. THE TIER STRIP at the bottom is the risk answer. Say: "We split delivery into three tiers so there is a working product at every milestone. If the semester goes badly we still ship the blue tier. If it goes well we ship all three." SAY THIS SENTENCE, VERBATIM, AND DO NOT IMPROVISE AROUND IT: "This is coarse inspection, several millimetres on hand-sized parts. It complements CMM inspection and does not replace it. It will never certify a tenth of a millimetre." Stating the limit before anyone challenges it is what makes the rest of the talk credible. LIKELY QUESTION: "Why not just buy a 3D scanner for a few hundred dollars?" ANSWER: "A scanner is more accurate on raw geometry, and a scan file emailed by the supplier is exactly as trustworthy as the supplier. Our output is a report tied to a specific purchase order, that records what was actually seen and what was not."

## Slide 6
Technology Stack (1/2)
Capture, hosting and the service layer
Layer | Choice | Fallback / notes
Front end | Progressive web app in TypeScript; getUserMedia (camera), DeviceOrientation (gyro), three.js viewer | HTTPS required for camera and sensors; Safari tab on iOS
Reference sheet | Printed ChArUco board on A4 / Letter with a per-PO QR code and orientation arrow | Blank sheet or credit card, with wider error bars
Board detection | OpenCV ≥ 4.7 ChArUco detector, solvePnP, QR detector; intrinsics calibrated from the board | Stock tooling, no custom detector
Backend service | Python 3.11, FastAPI, uvicorn, Docker | One image, one command
GPU hosting | RunPod RTX 4090 (24 GB) pod behind its HTTPS proxy; about $150–200 for the semester | Network volume + startup script for re-provisioning
Static hosting | Served from the same pod | GitHub Pages, or IBM LinuxONE for the application layer only
Storage | Folder + JSON per purchase order on the pod volume | No database this semester
Test rig | FDM 3D printer, digital calipers, calibration cube | Print service or a $200 printer
Mamadou
Notes: TIMING: 90 seconds. Do not read the table. Pick four rows. ROW 1, front end: "A progressive web app, so there is no install and no app store. The tradeoff is that the camera and motion sensors require HTTPS, which shapes our hosting choice two rows down." ROW 2, reference sheet: this is the one row worth explaining properly. "Photos recover shape but never size. Something of known physical size has to be in the frame. We print a ChArUco board, which is a checkerboard with a unique marker in each square. Every corner is individually identifiable, so a partly covered board still works, and it gives us a metric camera position for every single photo. On glossy parts with no texture, the board is also what keeps the camera tracking stable." Mention the fallbacks in one clause: a blank sheet of paper or a credit card, both with wider error bars. ROW 5, GPU hosting: "We rent, we do not request hardware. About one hundred fifty to two hundred dollars for the semester, on our own card if needed. That takes university procurement off our critical path entirely." LAST ROW: "The printer and calipers are how we know whether any of this is accurate." LIKELY QUESTION: "What if the rented pod is unavailable?" ANSWER: "The image is in a registry and the state is on a network volume, so re-provisioning is a one-command routine, not an emergency." If time is short, cut this slide to the reference sheet row alone and move on.

## Slide 7
Technology Stack (2/2)
Reconstruction, inspection and AI components
Phone frames
+ gyro
Board detection:
metric poses
VGGT
reconstruction
TSDF mesh
+ provenance
CAD registration
+ heatmap
Verdict
+ report
Stage | Choice | Fallback
Multi-view reconstruction | VGGT: feed-forward transformer; cameras, depth and point maps in one pass | MASt3R, then COLMAP
Fusion and meshing | Open3D TSDF volume + marching cubes; cleanup and GLB export | Open3D Poisson
Segmentation | Board-frame crop: keep points above the sheet plane | SAM 2 masks
CAD registration | Open3D FPFH + RANSAC, then robust ICP (Tukey loss); ambiguity check | trimesh ICP
CAD I/O, defect synthesis | trimesh + manifold3d Booleans; STL / OBJ / GLB input | STEP import is future work
Next-view scoring | Open3D RaycastingScene on CPU; no custom CUDA | Fixed 12–16 position orbit
Generative AI (core) | Capture agent (tool-calling loop), shape completion, VLM frame supervision, prose-to-spec parser | Deterministic policy; coverage-only guidance
Generative AI is 115 of our 349 person-hours, a third of the project: the capture agent, shape completion, frame supervision, the prose-to-spec parser and the report narrative. The reconstruction model is counted in that as a large learned model, though unlike the others it is deterministic.
Mamadou
Notes: TIMING: 2 minutes. This is the technical heart of the talk. WALK THE PIPELINE ACROSS THE TOP, one clause per box, do not stop: "Frames come off the phone with gyro readings. Board detection gives a metric camera pose for each frame. The reconstruction model turns the frames into geometry. We fuse that into a single mesh and record, per point, whether we actually saw it. We align the mesh to the CAD. That produces the heatmap and the verdict." THEN THE TWO ROWS THAT MATTER: Reconstruction: "Our primary is VGGT, a feed-forward transformer that takes all the frames at once and returns cameras, depth and point maps in a single pass. No iterative matching, so it is fast enough to be interactive. If it underperforms on our parts we fall back to MASt3R, and past that to COLMAP, which is the classical method and the most predictable." Provenance: "Every point in the mesh is labeled observed or unobserved. Observed means at least two frames actually saw it from angles far enough apart to triangulate." SAY THIS SENTENCE, VERBATIM. It is the rule that makes the report trustworthy: "Geometry we did not observe never fails a part and never contributes to a pass. It can only trigger a rescan." Explain why in one line: "A model that fills in a hidden surface is guessing. A guess must never approve or condemn a part." THE TEAL BOX AT THE BOTTOM. Do not skip this, it answers the course's one-third requirement. Read the number, then give the test: "Generative AI is a third of this project, a hundred and fifteen of three hundred and forty-nine hours. Our test for what counts is simple: if you run a component twice, can it give you two different answers? The agent, the shape completion, the frame supervision, the spec parser and the report narrative all can. The reconstruction model cannot, so we flag it as learned but deterministic rather than quietly folding it in." BE OPEN ABOUT THE BACKBONE before anyone challenges it: "We would welcome guidance on whether the reconstruction model should count. If it does we are at thirty-three percent. If it does not we are at twenty-five, and we would want to talk about what to change." IF ASKED whether the AI is bolted on: "No. The agent runs the capture session, a generative model imagines the surface the camera never saw and that decides where we ask for the next photo, and a vision-language model can veto a pass. Remove them and the product stops working." IF ASKED how the hours were found: "We raised our own commitment from eight hours a week each to nine, and spent every added hour on the AI work." LIKELY QUESTION: "Is the 3D model generated by AI?" ANSWER: "The geometry comes from real photographs through a learned reconstruction model, and every point is labeled by whether the camera actually saw it. Nothing invented contributes to the verdict." LIKELY QUESTION: "What is the licence on those models?" ANSWER: "Non-commercial research licences, which is fine for a capstone. Swapping the backbone later is one config flag."

## Slide 8
Timeline
Milestones are dated and gated; each names what works by the date and the fallback
Build the core · M0–M2 · Sept 8 – Oct 9
Measure and inspect · M3–M5 · Oct 16 – Nov 13
Test, harden, present · M6–M8 · Nov 16 – Dec 18
Milestone | Date | What works by this date
M0 · Spike | Tue Sep 8 | Phone photos on a printed board → metric mesh on a rented GPU; backbone chosen
M1 · End to end | Fri Sep 25 | Link → capture → upload → reconstruction → GLB in the browser; batch mode
M2 · Capture quality | Fri Oct 9 | Local gate, gyro arrow, segmentation, provenance map; latency table picks the mode
M3 · Accuracy baseline | Fri Oct 16 | Printer characterized; printed parts calipered; σ_floor per tier; defect ladder printed
M4 · Inspection | Fri Oct 30 | CAD registration, heatmap, verdict logic, hard rule, report page
M5 · Feature complete | Fri Nov 13 | Ingestion pre-check, sheet / card tiers; Tier 3 only if Tier 2 is done; feature freeze
M6 · Test and harden | Nov 16 – Dec 2 | Accuracy, planted-defect, robustness and usability tests; recorded demo
M7 · Freeze | Fri Dec 4 | Code freeze; report and slides
M8 · Final | Dec 7–18 | Presentation, live demo, recorded backup
Yashi
Notes: TIMING: 2 minutes. Do not read nine rows. Use the three bands, then four rows. Point at the bands: "Build the core, then measure and inspect, then test and present." M0, September 8, next week: "Before we commit to this topic we prove the pipeline works. Photos of any rigid object on a printed board, through a rented GPU, out as a measured mesh. If the primary model fails, that is when we switch, not in November." M1, September 25: "A phone on this team completes a full session end to end. That is Tier 1 existing in its simplest form, in week four." M3, October 16: "We stop guessing about accuracy. Printer characterized, parts printed and measured with calipers, sigma-floor measured per reference tier. Every threshold in the product is set by this measurement." M5, November 13: "Feature freeze. Anything not working by then is cut, not deferred into finals week." Then the bottom line: "Three of us, about eight hours a week each, roughly three hundred ten person-hours. Labor Day and Thanksgiving are already accounted for. Thanksgiving week is bug fixing only." LIKELY QUESTION: "What happens if the reconstruction quality is poor?" ANSWER: "Two model fallbacks behind one flag, and a batch mode that always works even if interactive guidance does not. The failure boundary itself, which surfaces and finishes defeat the method, is a reportable result." LIKELY QUESTION: "Is this too ambitious for one semester?" ANSWER: "That is why it is tiered and why we have a written cut list in priority order. The core is a working capture-to-model pipeline, and that is proven next week at M0."

## Slide 9
Who Builds What, and When
Three people working in parallel from September to December
SEPTEMBER
OCTOBER
NOVEMBER
DECEMBER
M1 First 3D model
M3 Accuracy measured
M4 Pass / fail works
M5 Feature freeze
M8 Final demo
WE PRESENT
PERSON A
Capture app
Capture app + camera
Guidance + quality
Heatmap + report screens
Phone testing
PERSON B
3D reconstruction
Pick 3D engine + service
Build the mesh
Tuning, scale checks, backups
Reliability
PERSON C
Inspection + testing
Print test parts + align to design
Measure accuracy
Pass / fail logic
Run all the tests
ALL THREE
Shared
Record demo
Report + present
Person A
Person B
Person C
All three
Milestone
Class review
Must finish first
We report progress every two weeks. Each circle is a class presentation, and each one follows a milestone by a few days, so we are always showing work that is finished rather than work from that morning. The arrow marks the one hand-off: Person B's 3D model must work before Person C can measure its accuracy.
Yashi
Notes: TIMING: 90 seconds. Presenter: whoever owns the schedule. Assume nobody in the room has seen a Gantt chart for this project before. Teach the axes first, then the one thing that matters. HOW TO READ IT, say this before anything else: "Time runs left to right, September on the left, our final demo on the right. Each row is one person. Each bar is a block of work, and the length of the bar is how long it takes." WHAT THE COLORS MEAN, one line: "One color per person. Blue is [Team member 1] on the capture app, green is [Team member 2] on the 3D reconstruction, orange is [Team member 3] on inspection and testing, grey is all three of us together." THE POINT OF THE SLIDE. Everything above is setup. This is the sentence to land: "Almost every bar runs in parallel. That is deliberate. We designed the work so the three of us are never waiting on each other, because with eight hours a week each we cannot afford a week of one person blocked." THE ARROW. Point at it. "There is exactly one hand-off we could not design away. [Team member 2] has to get the 3D model working before [Team member 3] can measure how accurate it is, and that accuracy measurement is what sets the pass and fail limits. So that chain, mid-October, is the one place a delay pushes the finish date." THE DIAMONDS AND THE CIRCLES. These are different things, say so clearly: "The diamonds are our internal checkpoints, where we stop and wire the three pieces together and confirm they work as one system. The open circles are when we present progress to this class. Seven of them, every two weeks." WHY THE CIRCLES SIT WHERE THEY DO. This is worth one extra sentence, because it shows the schedule was designed rather than assumed: "We lined the presentations up so each one lands a few days after a checkpoint closes, not on top of it. That way we are always demonstrating something that has been working and tested for a few days, rather than something that started working that morning." IF ASKED what we show at each one: "The same four slides every time. What we said we would do, what works now with a live demo, what slipped and why, and what we will have by the next one." IF THEY ASK how the rest stays parallel: "Three cheap stand-ins, built in the first two weeks. A written interface agreement so the app and the server can be built against the same spec before either exists. One saved set of photographs so the reconstruction work never waits for the phone app. And a script that fakes a 3D model so the inspection logic can be built and tested months before the real reconstruction is ready." LIKELY QUESTION: "What happens if someone falls behind?" ANSWER: "We have a written cut list in priority order, agreed in advance, so we cut features in a known sequence rather than arguing about it in November. The core, phone photos to a 3D model, is never on that list." LIKELY QUESTION: "Why is there slack at the end?" ANSWER: "That is not slack, it is testing and hardening. We freeze features in mid-November on purpose, so the last three weeks are fixing and rehearsing rather than building." DO NOT read the bars aloud one by one. The audience can see them.

## Slide 10
References
Models, libraries and standards the project builds on
1. Wang, J., Chen, M., Karaev, N., Vedaldi, A., Rupprecht, C., Novotny, D. "VGGT: Visual Geometry Grounded Transformer." CVPR 2025. arXiv:2503.11651
2. Leroy, V., Cabon, Y., Revaud, J. "Grounding Image Matching in 3D with MASt3R." ECCV 2024. arXiv:2406.09756
3. Wang, S., Leroy, V., Cabon, Y., Chidlovskii, B., Revaud, J. "DUSt3R: Geometric 3D Vision Made Easy." CVPR 2024. arXiv:2312.14132
4. Schönberger, J. L., Frahm, J.-M. "Structure-from-Motion Revisited." CVPR 2016. (COLMAP)
5. Zhou, Q.-Y., Park, J., Koltun, V. "Open3D: A Modern Library for 3D Data Processing." arXiv:1801.09847, 2018
6. Garrido-Jurado, S., Muñoz-Salinas, R., Madrid-Cuevas, F. J., Marín-Jiménez, M. J. "Automatic generation and detection of highly reliable fiducial markers under occlusion." Pattern Recognition 47(6), 2014. (ArUco / ChArUco)
7. Curless, B., Levoy, M. "A Volumetric Method for Building Complex Models from Range Images." SIGGRAPH 1996. (TSDF fusion)
8. Kazhdan, M., Bolitho, M., Hoppe, H. "Poisson Surface Reconstruction." Symposium on Geometry Processing, 2006
9. Rusu, R. B., Blodow, N., Beetz, M. "Fast Point Feature Histograms (FPFH) for 3D Registration." ICRA 2009
10. Ravi, N., et al. "SAM 2: Segment Anything in Images and Videos." arXiv:2408.00714, 2024
11. Bai, S., et al. "Qwen2.5-VL Technical Report." arXiv:2502.13923, 2025
12. ISO/IEC 7810:2019. Identification cards — Physical characteristics. (credit-card reference dimensions)
13. Tools and services: OpenCV (opencv.org), three.js (threejs.org), FastAPI (fastapi.tiangolo.com), trimesh (trimesh.org), Manifold (github.com/elalish/manifold), RunPod (runpod.io), Google Gemini API (ai.google.dev)
Notes: TIMING: 20 seconds. Do not read the list. This is the last slide before questions. Say: "The reconstruction, fusion and registration methods are all published and have open implementations. We are integrating known components into a working product, not inventing the geometry from scratch." Then hand to Q&A. Q&A BANK, short answers ready: "How accurate is it?" - "We do not have that number yet, and we will not guess. We measure it at M3 against caliper ground truth on printed parts. Our design target is several millimetres on hand-sized parts." "How is this different from an app that makes a 3D model?" - "Two things: it is metric, because the printed sheet supplies real-world scale, and it reports what it did not see instead of quietly filling it in." "How many photos, and how long?" - "Ten to thirty photos, targeting under two minutes of capture, and seconds to reconstruct on the rented GPU. The timings get measured at M2." "What if the supplier cheats?" - "Optional and honestly bounded. The sheet carries a per-order code so old photos cannot be replayed, and a photo of a screen reconstructs as a flat plane, which we detect. It does not prove which physical unit of an identical part is on the sheet, and we say so in the report." "Is there a user study?" - "An informal one with five or six volunteers, internal only, so no IRB approval is needed this semester. A formal study with IRB approval is future work." "What is the research contribution?" - "The capstone deliverable is the product. The follow-on research question is whether capture should stop when enough of the surface is covered, or when the scan can demonstrably detect the defects the buyer cares about. We build the product half of that this semester." IF YOU DO NOT KNOW AN ANSWER: say "We do not know yet, that is what M3 measures." Do not invent a number. The credibility of this proposal rests on not promising numbers we have not measured.